## Sheet1
Sr.No | STEPS for Migraton Activity | Type
Phase I
1 | Take details from OLD Server | Pre-Requisite
2 | OS Configuration | Pre-Requisite
3 | SQL Version | Pre-Requisite
4 | Disk Space Details | Pre-Requisite
5 | Logins | Pre-Requisite
6 | Linked Servers if any | Pre-Requisite
7 | Maintenance Plan | Pre-Requisite
8 | SQL Jobs | Pre-Requisite
9 | Any TDE Certificate | Pre-Requisite
10 | Port Information | Pre-Requisite
11 | Number of Databases User | Pre-Requisite
12 | File Details and Folder Structure | Pre-Requisite
13 | Database Options and Configuration | Pre-Requisite
14 | Alerts Details | Pre-Requisite
15 | Database Mails Details | Pre-Requisite
16 | Physical Files for System Databases | Pre-Requisite
17 | Physical Files for User Database | Pre-Requisite
18 | Backup for User and System Databases | Pre-Requisite
Phase II
1 | Preparing the New Server | Preperation Phase
2 | Check the OS Version and Patch Level | Preperation Phase
3 | Check if Best practices are in place | Preperation Phase
4 | Paging File | Preperation Phase
5 | Power Options | Preperation Phase
6 | BIOS Updates | Preperation Phase
7 | SQL Installable | Preperation Phase
8 | Drives for SQL Installation, Data, Log & Backup Drives | Preperation Phase
9 | SQL Service Accounts | Preperation Phase
10 | Permissions to SQL Service Account | Preperation Phase
11 | Group Policy | Preperation Phase
12 | Folder Level Permission | Preperation Phase
13 | SQL Patches as per Old Server | Preperation Phase
14 | Share to Copy Backup and Database Files | Preperation Phase
Phase III
1 | Post Check for Preparation Phase and Pre-Requisites Part | Installation Phase
2 | Install SQL Server on New Server | Installation Phase
3 | Install Patch Set for SQL Server matching the OLD Server | Installation Phase
4 | Restart the Server post installation | Installation Phase
5 | Install SSMS on New Server | Installation Phase
6 | Take Backup for System Databases | Installation Phase
7 | Check for MSSQL Binnary Location, Physical database files path | Installation Phase
Phase IV
1 | Lets decide on how to Migrate the Data | Intiation Phase
2 | Log-Shipping/Backup & Restore in no recovery | Intiation Phase
3 | Take Log Backup for SQL Server User Databases | Intiation Phase
4 | Put them in Single User | Intiation Phase
5 | Detach the databases from Old Server | Intiation Phase
6 | Stop the SQL Server on OLD Server now | Intiation Phase
7 | Copy the Sytem Databases Physical Files from OLD Server to Share Drive | Initiation Phase
Phase V
1 | Go to the New Server and Copy Old Master Physical Files | Implementation Phase
2 | Take Backup for New Server Master Databases & other System DB | Implementation Phase
3 | OverWrite the master DB Files to the New Server | Implementation Phase
4 | Start the SQL Server in using Trace Flag 3608 | Implementation Phase
5 | Check the ErrorLogs for any Errors | Implementation Phase
6 | Rectify them if any | Implementation Phase
7 | Create Folder Structure as per OLD Server or restore DB using Move option to new File structure Provided. Provide Permissions to Folders for Service Account | Implementation Phase
8 | After Restoration Ensure we have latest backup taken for SQL Server User and Sytem DB on New Server | Implementation Phase
9 | Verify the Configurations taken in Pre-Requisite Phase | Implementation Phase
10 | Kindly add if you find anythings missing | Implementation Phase
11 | Restart the SQL Server when everything is in place | Implementation Phase
12 | Do complete Health Check | Implementation Phase
| Database Online | Implementation Phase
| Drive Space | Implementation Phase
| Log Space | Implementation Phase
| Errorlogs | Implementation Phase
| Check for Alerts, Jobs etc | Implementation Phase
13 | Ensure you do run the maintenance Jobs post completion of Activity | Implementation Phase
| Index Optimize with Update Statistics | Implementation Phase
| DBCC CheckDB | Implementation Phase